President’s Dinner Creative Committee

Brief Meeting Notes

Date: Wednesday 11 February 2026 at 8pm (via Teams)

Present: Clare Booth, Jenn Birrell, Gina Fusco, Sue Westacott, Claudine Pearson

Event Summary:

- Date: Saturday, 18 April 2026

- Theme: Henley Royal Regatta – Club Heritage & Elegance

- Foundation: Builds on 150th Anniversary; focus on Club future

- Planning Start: 19 January 2026

What Works / Agreed Ways of Working

- Meeting notes to be shared on website.

- Use WhatsApp group (avoid email).

- Meetings: Wednesdays work best; next meeting: 25 February.

- Proposed venue walk-through: Thursday at Welcombe Hotel with Paul.

- Set-up/decor: to confirm with venue.

Presidents Dinner - Creative Committee
20:00 - 21:00 (GMT)
Occurs every 2 weeks on Wednesday starting 28/01 until 15/04

Meeting link: Presidents Dinner - Creative Committee | Microsoft Teams | Meetup-Join

Meeting ID: 931 942 677 972 5

Passcode: F2HP6z

February 2026 – Kick-Off

Committee & Roles

- Secretariat to brief all sections/committees on proposal and dates (clarify section leads – Claudine).

- Key leads identified:

  - Logistics: Claudine

  - Speakers:

    - Section representatives to reflect on Paul’s time.

    - Esme (junior perspective).

    - Club representative on Paul’s presidency – Dawson (speech support offered).

    - Ed to be asked to speak.

    - Graham to suggest early-days anecdotes.

    - Gina to ask Tracy.

    - Mark Dewdney to be asked for Henley memories and possible speech (short synopsis requested).

  - Fundraising / Comms / Sponsorship: Not yet assigned (to be confirmed).

Creative & Décor

- Bunting: Jenn to check; Clare has GB bunting.

- Oars / crossed blades at entrance.

- Tables: 15 centrepieces (Karl).

- Place cards: Sue W.

- Top table: speakers + Paul & Jan (to confirm).

- Linen: check napkin colours.

- Flowers/vases: Anna to consider.

- Photo assets: existing frames; Sue to explore photo presentation.

- Gifts for Paul: Gina to ask Dawson.

- Games/croquet: likely limited space (check feasibility).

- Selfie frame: find.

Reuse & Recycle

- Review 150th Anniversary assets (bunting, oars, tent, games, blankets).

Fundraising

- Update sponsorship package (limited due to seating).

- Begin appeal for local donations and club promises.

- Define raffle framework, prizes, and ticket handling (owner TBC).

- Clarify fundraising priorities and targets.

Budget & Tickets

- Consider “early supporter” / “table host” incentives

- Seating plan: confirm numbers per table; explore selling a full table.

- Ticketing: TicketSource – noted that a fee is deducted. Claudine to confirm return.

Venue & Logistics

- Reconfirm booking, menus, and arrangements with Welcombe Hotel.

Communications

- Save-the-Date to be designed using 150th style; distribute via WhatsApp/email/noticeboard.

- VIPs: compile alumni list and issue invitations per MMC agreement.

Actions Before Next Meeting (25 Feb)

- Confirm section leads and unassigned roles.

- Liaise with Paul on speakers

- Explore gift suggestions

- Confirm offer to lifetime members

- Arrange venue visit date/time.

- Progress speaker invitations.

- Start décor and asset inventory.

- Agree responsibilities.